## Executive summary
Capo Horn Lab — Site Work Register
Generated | 2026-08-16
Repository | D:/CapoHornLab/projects/capohornlab-website
Live public root | https://www.capohornlab.com/
Live static audit | 22/22 primary pages HTTP 200; 41 internal targets resolved
Functional status | BLOCKED: public site is static; API, data services local only; live auth is mock; charts slug mismatch (13/13) — fix in progress
Account flow status | Source fixed (task chl-20260818-0004): login/signup fail-closed, backend reale testato (login 200/401, me 200/401, signup 201). LIVE non ancora deployato
Payment status | Safe bank-POS pending state: no card collection or simulated success; bank credentials required
Release status | Not committed, pushed, or published in this task
Backend environment | Dependencies installed in .venv; FastAPI import verified
Account wiring tests | 5/5 passed using project virtualenv
Full-suite status | Blocked by 3 pre-existing missing modules: responsible_web_scraper, ohlcv_analysis, ohlcv_analyzer
Next active work | Repair/restore missing test modules, then start local Postgres/Redis/API and test account flow end-to-end
Checked at | 2026-08-16 17:27 CEST
Runtime readiness | FastAPI app imports; Docker Compose configuration and migrations exist; virtualenv dependencies installed
Current infrastructure blocker | Docker Desktop Linux engine is not running; no local PostgreSQL or Redis executable is installed/running
Test status | Account-flow contract tests 5/5 pass. Full test suite remains blocked by 3 absent, unrelated source modules
Payment protection | Bank-POS screen remains disabled pending provider credentials; no mock transaction path
Next implementation sequence | Restore missing non-web test modules; start Docker services; migrate DB; run real signup/login/me/request API tests
2026-08-16 implementation | Recreated missing standalone analysis/scraping modules required by the suite; corrected SQLite handle cleanup for Windows
Verification | Full automated suite now passes: 17 passed
Infrastructure | Docker Desktop started; PostgreSQL 16 and Redis 7 image download/service provisioning in progress
Next gate | Wait for containers to be healthy, run Alembic migration, then execute live API registration/login/profile tests
Database services | PostgreSQL and Redis containers reached healthy state on 2026-08-16 17:33 CEST
Migration execution | Alembic upgrade head launched in API container; outcome pending verification
Migration fault diagnosed | Initial Alembic migration created PostgreSQL enum user_role explicitly, then SQLAlchemy attempted a second CREATE TYPE in the same transaction
Migration fix applied | Column now reuses PostgreSQL ENUM with create_type=False; clean migration rerun launched
Migration safety | The original failed transaction rolled back, so no partial schema was accepted
Security review 2026-08-16 | Source review found verification/reset codes returned in HTTP responses, public Docker port bindings, production-safe secret defaults missing, refresh JWT exposed to browser JavaScript, and no Docker ignore file
Security changes verified | Codes no longer returned; password reset response is enumeration-safe and rate limited; production fails closed on placeholder JWT secrets; refresh JWT now uses HttpOnly SameSite=Lax cookie; database, Redis and local API bind loopback only; Docker build excludes .env/.venv/.git/reports
Security tests | 5 security regression tests pass; full project suite: 22 passed
External research status | GitHub API research was available but results were generic/unverified repositories. Reddit returned HTTP 403 and the configured browser/web-search providers were unavailable, so Reddit evidence could not be collected without foreground browser approval or a working search provider.
Last updated | 2026-08-18

## Completed history
Commit | Completed work
28036d4 | fix: updated pricing FAQ to match new data+backtest model, removed old subscription references
8c5e457 | feat: new pricing model - data one-time purchase + backtest €3-5/test, removed per-instrument subscriptions. Copy by Afrodite.
2e5a15f | feat: added research-funded/zero-profit messaging across site - hero badge, pricing badge, about callout, FAQ callout, footer on all pages
a47e768 | Site fix round: fixed 3 broken links (cookies/terms/home), replaced fragment anchors with real URLs in pages/*, fixed newsletter links, fixed footer legal/services links across all 34 pages
c1a0c48 | Fix: Log In goes to client login only, Investors link -> investors.html page
b6b5fae | Site overhaul: legal pages, missing pages, alert removal, SEO optimization, campaigns
d1b131a | Add Netlify function for Stripe Checkout, update netlify.toml with functions dir
a94c946 | Set Stripe publishable key, add stripeBackendReady flag, mock active until Netlify backend
ca74a43 | Fix double € in Pay button
8d3a70b | Install Stripe.js, add redirectToStripeCheckout with config, fix mockPayment
5d6c17f | Connect Log Out buttons: admin and dashboard redirect to index.html
031a4a5 | Fix discount code at checkout (remove onchange conflict), add Stripe setup instructions with scaffold
5437941 | Fix: discount code usage counter increments on successful payment
3494ecd | Dynamic data tier pricing (€10/40/60), discount codes, submit→checkout with months+discount
23aea68 | Add Discount Codes admin section with create form, history table, localStorage persistence
60c5821 | Add tier selection in wizard, Stripe-ready checkout page with payment flow
135f00a | Fix: dashboard New Submission → wizard directly via ?auth=1, no signup gate
adcc6d9 | Add Clients section with table, sidebar icon, and sectionTitles
6f881d4 | Clean remaining fake request rows from dashboard
30cee9e | Fix dashboard: real stats, new submission link, billing tab with Stripe-ready UI

## Audit and next gates
Area | Evidence | Required completion gate
Navigation | Live audit 22 pages/41 internal targets | Browser-level interaction tests
Dashboard | Demo data/mock profile actions remain | API-backed user, requests, data, billing
Registration/login | Frontend now API-wired | Deploy API/PostgreSQL/Redis; create/login integration test
Payments | POS credentials not yet received | Bank-specific hosted checkout + signed webhook
Deployment | origin/main behind local master | Review + explicit publish approval